Proposed Amendments to Active Project Scope, Budget and Schedule due to Additional Project Funding from Yakima Basin Integrated Water Plan Administered by WA Department of Ecology

To: 	Washington State Salmon Recovery Funding Board, RCO, Olympia

c/o Tara Galuska, Brian Abbott, Kay Caromile

Date:		August 15, 2013

Project Title & Number:  Gold Creek Habitat Assessment + Conceptual Design, 12-1306

Project Sponsor: Kittitas Conservation Trust, POB 428 Roslyn WA 98941, 509-649-2951

Sponsor Contacts:  	 David Gerth     kct@inlandnet.com

Mitch Long      brooksideprojectmanagement@gmail.com

Background:	Kittitas Conservation Trust is actively implementing the Gold Creek Assessment project using RCO/SRFB funds with associated contractual goals, specifications and deliverables. The Period of Performance of the Salmon Project Agreement is 12/6/2012 – 12/31/2014. Initial hydrological data has indicated a need for expansion of the project’s scope, budget and schedule in response to the magnitude and complexity of the habitat degradation issues in the Gold Creek project area. The project was selected to receive an additional $50,000 in grant funding from Washington State Department of Ecology (Ecology) for habitat enhancement or water conservation projects under the Yakima Basin Integrated Water Resource Management Plan (Integrated Plan). The IWP grant funding is being administered through the RCO/SRFB project process.

Project Description:	Kittitas Conservation Trust will assess salmonid habitat in the Gold Creek watershed and produce a habitat restoration conceptual design. Gold Creek is a head waters tributary to the upper Yakima River that originates in the Alpine Lakes Wilderness and then flows into Lake Keechelus near Snoqualmie Pass in northern Kittitas County (WRIA 39). The primary goal of the assessment is to investigate the causes of Bull Trout mortality such as seasonal dewatering, spatial constraints and habitat degradation, then design restoration actions that employ natural fluvial processes to reverse the decline in at-risk Bull Trout populations.

Project Status:		Natural Systems Design has been contracted to implement the Gold Creek Habitat Assessment by completing the tasks in the following Scope of Work:

TASK 1: DATA INVENTORY

Compile and review existing data and information from previous investigations relevant to the Gold Creek assessment.  Critical data sources will focus on describing the processes most directly impacting the stream:  sediment supply, sedimentation, bank strength and riparian conditions, surface and subsurface water flow, in-stream and floodplain habitat, presence and function of wood, and human impacts to the fluvial system (e.g., stream bank impacts, drainage modifications, floodplain ponds).

TASK 2: HYDROLOGIC SURFACE AND SUBSURFACE ASSESSMENT

Conduct a hydrologic monitoring investigation to collect new data supporting an analysis of the spatial and temporal variation of surface water-groundwater interactions.  Findings of this investigation will be utilized in conjunction with the geomorphic assessment to develop design solutions to address the negative impacts of seasonal dewatering on the Gold Creek Bull Trout population.  This Task is the single most important and time consuming due to the manpower needed to install and monitor piezometers and data recording instruments.

TASK 3: GEOMORPHIC ASSESSMENT

A geomorphic assessment will be completed to characterize prevailing conditions within the Gold Creek watershed to identify key drivers affecting the channel response potential in the project reach.  This assessment will utilize existing information and GIS data to describe basin scale characteristics and identify potential source, transport, and response reaches.

TASK 4: HABITAT ASSESSMENT

Evaluate the effects of both natural and human induced changes on channel, riparian and floodplain conditions.   A field survey will be conducted to inventory key habitat features within Lower Gold Creek.  The locations and functions of these features will be used to evaluate current conditions and document mechanisms contributing to and degrading habitat conditions.

TASK 5: CONCEPTUAL DESIGN

The findings of the hydrologic, geomorphic and habitat assessments will be integrated and used to inform the development of up to 3 conceptual design alternatives that achieve the restoration goals in a way that is based on natural processes and provides a self-sustaining long-term solution that is compatible with the local community and site constraints.

TASK 6: MEETINGS AND STAKEHOLDER COMMUNICATION

To ensure communication between the design team, KCT, the Yakima basin technical work group, project stakeholders and the local community, several meetings will be required.  The agenda and scheduling for each meeting will be led by KCT, with input from NSD as requested.

TASK 7: PROJECT MANAGEMENT & EXPENSES

This task includes the labor and expenses associated with scheduling, coordination, and quality control services for this work.

Revised Project Scope and Budget:

| Current Scope | Current Budget | Expanded Scope Details | Proposed Budget |
| --- | --- | --- | --- |
| TASK 1 – Data Inventory and Gap Analysis | $ 6,860 | Review, inventory and catalogue additional studies and reports | $ 8,860 |
| TASK 2 – Hydrologic Surface and Sub-Surface Water Assessment | $ 31,950 | Install up to 6 additional monitoring wells, 4 additional recording transducer staff gauges | $ 48,850 |
| TASK 3 – Geomorphic Assessment | $ 11,400 | LIDAR flight, additional field work under expanded schedule | $ 20,200 |
| TASK 4 – Habitat Assessment | $ 7,060 | Study area expansion requiring additional field work | $ 10,070 |
| TASK 5 – Conceptual Design | $ 24,560 | Scope expansion to 4 restoration action alternatives | $ 31,556 |
| TASK 6 – Meetings and Stakeholder Communications | $ 19,980 | Additional stakeholder and Technical Work Group meetings to review alternatives & comment | $ 21,980 |
| TASK 7 – Project Management , Expenses | $ 23,484 | No change | $ 23,484 |
| Total | $ 125,294 |  | $ 165,000 |

Fiscal resources currently committed to the Gold Creek Habitat Assessment Project:

$ 97,750	Salmon Recovery Funding Board (12-1306)

$ 10,000	US Fish & Wildlife Service (ESA) Assistance Agreement

$ 7,250	Kittitas Conservation Trust (in-kind labor & project management)

$ 115,000    Total available- current Project Funding

Secured fiscal resources for expanded project scope:

$ 97,750	Salmon Recovery Funding Board (12-1306)

$ 10,000	US Fish & Wildlife Service (ESA) Assistance Agreement

$ 7,250	Kittitas Conservation Trust (in-kind labor & project management)

$ 50,000	Yakima IWP project assistance

$ 165,000    Total available- expanded Project Funding

Project Schedule:  The term of the SRFB grant agreement is requested to be amended to 12/06/2012 through 06/01/2015 with the following Milestones.

August 15, 2013 Proposed Revised Project Schedule Milestones

Project Number:	12 – 1306 P

Project Name: 	Gold Creek Habitat Assessment and Conceptual Design

Sponsor: 	Kittitas Conservation Trust

| Milestone | Target Date | Comments Description |
| --- | --- | --- |
| Project Start | 12/06/2012 |  |
| Data Gathering Started | 02/01/2013 | Eligible pre-agreement expenses per Manual 18 (2011) page 65 |
| RFQ Complete/Consultant Hired | 03/01/2013 | RFQ released 12/15/12 to 17 habitat consultants. Natural Systems Design awarded contract. |
| Assessment design and scope complete | 05/01/2013 | Includes project plan, itemized tasks and schedule |
| Progress Report Submitted | 06/01/2013 |  |
| Hydrologic Monitoring Devices Deployed | 07/01/2013 | Monitoring wells and Surface water gauges |
| Data Gap Analysis Complete | 12/01/2013 |  |
| Preliminary Habitat Analysis Memo | 12/01/2013 | Based on 2013 hydrologic data |
| Progress Report Submitted | 12/01/2013 |  |
| Hydrologic Monitoring Plan for 2014 | 03/31/2014 | Respond to analysis of 2013 hydrologic data |
| Progress Report Submitted | 06/01/2014 |  |
| Draft Habitat Analysis & Conceptual Restoration Design Alternatives | 11/01/2014 | Technical Work Group and stakeholder presentations |
| Progress Report Submitted | 12/01/2014 |  |
| Cultural Resources Complete | 12/01/2014 | Project included in RCO EO 05-05 consultation. Cultural Resources survey completed 9/15/2011 |
| Restoration Design Alternatives Review | 03/01/2015 | Technical Work Group Presentations |
| Final Design to RCO | 06/01/2015 | Conceptual Design deliverables as described in Appendix D-1, Manual 18 (2012) |
| Final Plan to RCO | 06/01/2015 | Feasibility Study deliverables as described in Appendix D Manual 18 (2012) |
| Agreement End Date | 06/01/2015 | PROJECT CLOSING. All expenditures must be prior to this date. |
| Final Report in PRISM | 06/30/2015 | Yakima IWP Project completion |
| Final Billing to RCO | 08/01/2015 | Provide your final invoice and report within 60 days of Agreement End Date. |

Project Deliverables:  Conceptual Design Deliverables

The following deliverables will be submitted to SRFB grants manager along with any assessment and feasibility deliverables funded in the scope of work.

1. Description of the project site and the problem(s) within the context of salmon recovery;

2. Identification of specific goals and objectives for addressing the problem(s);

3. Identification and conceptual design of alternatives for achieving the project objectives. Each conceptual design alternative will include a description of the design and a plan view drawing of existing site conditions and the proposed project on accurately scaled site plans. The plan view drawing will include: an area/location map; property boundaries (either surveyed or approximated based on assessor’s data); landownership; roads or other infrastructure as appropriate; scale; north arrow; water bodies and direction of flow; bank-full width or mean high water line for marine waters; and approximate dimensions of proposed elements;

4. Evaluation and discussion of stakeholder comments and the pros and cons of each alternative;

5. Selection of the preferred alternative(s); and

6. Rough construction cost estimate of the preferred alternative(s).