## WorkPlan
Work Plan, Schedule and Estimated Costs by Task for the Asotin IMW - October 1, 2013 to Sept 30, 2014*
Start Date | End Date | Task/Personnel | Description and Rational | Cost Estimates
Eco Logical Research Inc.
2013-10-01 | 2014-09-30 | Project Management, Data Management, Coordination, Data Analysis, and Reporting/ Project Manger; GIS, Statistical, and Database support staff | Management of overall project goals including coordination, permitting, budget and work plan development and tracking; manage PIT tag, fish capture data, PTAGIS and array resight data; coordinate with CHaMP to upload and analyze habitat data; manage LiDAR and aerial photography; provide monthly progress and annual reports; manage temperature and discharge data; synthesis and interpret data and test effectiveness of restoration using statistical models. | 100000
2013-10-01 | 2014-09-30 | Fish and Habitat Monitoring/ Crew of one Sr and three Jr Technicians for 5-7 months | Monitor permanent sites for fish abundance, growth, survival, and movement, and habitat condition (CHaMP habitat protocol, photo documentation, rapid habitat surveys), maintain PIT tag arrays, temperature probes, water level gauges; conduct mobile fish surveys in winter and spring | 70000
2013-10-01 | 2014-09-30 | Acquire, Purchase, Maintain equipment and supplies | Purchase or rent equipment to conduct surveys (5000 PIT tags and supplies, electrpshockers, seine nets, waders, total stations, mapgrade GPS, etc), travel and vehicle expenses, utilities (power, internet and phone lines for PIT tag arrays and field house), accommodation and meals | 35000
subtotal ELR |  |  |  | 205000
Washington Department of Fish and Wildlife
2013-10-01 | 2014-09-30 | WDFW cooperation and support of IMW Project | WDFW provides two people to support fish and habitat survey and restoration activities; specifically sample 12 fish sites 4 times (2 summer and 2 fall) and aid in habitat monitoring, maintenance of monitoring infrastructure, and/or restoration activities
subtotal WDFW |  |  |  | 50000
sub-total ELR and WDFW |  |  |  | 255000
2013-10-01 | 2014-09-30 | Walla Walla Community College Contract Monitoring Fee | WWCC provides contract monitoring for the IMW project (6% of 1.06 x 198,000) | 11207.5472
TOTAL |  |  |  | 266207.5472
* because the available funds are less than the project costs we will work with SRSRB to prioritize activities and maintain long-term data streams based on available funds.