## Sheet1
Work Plan, Schedule and Estimated Costs by Task for WDFW Assistance for Asotin IMW - Oct 1, 2014 to Sept 30, 2015
Start Date | End Date | Task/Personnel | Description and Rational | Budget Request
Washington Department of Fish and Wildlife - subcontract to support IMW data gathering
2014-10-01 | 2015-09-30 | WDFW Management of data collected for IMW | Oversee tasks and manage data collected by WDFW for IMW; coordinate with IMW coordinator as needed; provide all data to IMW coordinator | 1314
2014-10-01 | 2015-09-30 | Monitoring | Conduct fish surveys at pre-defined upper sites in Charley, North Fork, and Sout Fork Creeks; assess fish movement on mianstem of Asotin Creek above and below Headgate dam; deploy approximatley 1000 PIT tags in mainstem and tributaries to support above efforts; maintain PIT tag antenna system in Asotin Creek; GPS redds when possible | 13698
2014-10-01 | 2015-09-30 | Expenses | cover direct costs of 1000-1300 PIT tags, reading scale samples for up to 700 juvenile steelhead, and miscellaneous supplie | 5488
subtotal WDFW |  |  |  | 20500