## ELR WorkPlan
Work Plan, Schedule and Estimated Costs by Task for the Asotin IMW - Oct 1, 2014 to Sept 30, 2015
Start Date | End Date | Task/Personnel | Description and Rational | Budget Request
Eco Logical Research Inc. - IMW Management, Coordination, Implementation and Synthesis
2014-10-01 | 2015-09-30 | Project Management, Data Management, Coordination, Data Analysis, and Reporting/ Project Manger; GIS, Statistical, and Database support staff | Management of overall project goals including coordination, permitting, budget and work plan development and tracking; manage PIT tag, fish capture data, PTAGIS and array resight data; coordinate with CHaMP to upload and analyze habitat data; manage LiDAR and aerial photography; provide monthly progress and annual reports; manage temperature and discharge data; synthesis and interpret data and test effectiveness of restoration using statistical models. | 72000
2015-01-01 | 2015-09-30 | Analyst | Data analyst to analyse all CHaMP, temperature, dishcarge, and fish data and to help develop models for testing effectiveness of restoration | 48960
2014-10-01 | 2015-09-30 | Fish and Habitat Monitoring/ **** Crew of one Sr and three Jr Technicians for 5 months | Monitor permanent sites for fish abundance, growth, survival, and movement, and habitat condition (CHaMP habitat protocol, photo documentation, rapid habitat surveys), maintain PIT tag arrays, temperature probes, water level gauges; conduct mobile fish surveys in winter and spring (5 field techs and 1 biologist) | 75000
2014-10-01 | 2015-09-30 | Acquire, Purchase, Maintain equipment and supplies | Purchase or rent equipment to conduct surveys (5000 PIT tags and supplies, electrpshockers, seine nets, waders, total stations, mapgrade GPS, etc), travel and vehicle expenses, utilities (internet at field house and PTAGIS upload charges by QCI), accommodation and meals | 22383.22
subtotal ELR |  |  |  | 218343.22
2014-10-01 | 2015-09-30 | RCO manages utility charges forPIT tag array infrastrucutre | Four power and phone line annual utility charges | 4200
sub-total Utilities payed by RCO |  |  |  | 4200
sub-total ELR, WDFW, and Utilities |  |  |  | 222543.22
2014-10-01 | 2015-09-30 | RCO overhead | RCO provides contract monitoring for the IMW project (4.12%) | 9168.7807
TOTAL |  |  |  | 231712.0007

## WDFW WorkPlan
Work Plan, Schedule and Estimated Costs by Task for WDFW Assistance for Asotin IMW - Oct 1, 2014 to Sept 30, 2015
Start Date | End Date | Task/Personnel | Description and Rational | Budget Request
Washington Department of Fish and Wildlife - subcontract to support IMW data gathering
2014-10-01 | 2015-09-30 | WDFW Management of data collected for IMW | Oversee tasks and manage data collected by WDFW for IMW; coordinate with IMW coordinator as needed; provide all data to IMW coordinator | 1314
2014-10-01 | 2015-09-30 | Monitoring | Conduct fish surveys at pre-defined upper sites in Charley, North Fork, and Sout Fork Creeks; assess fish movement on mianstem of Asotin Creek above and below Headgate dam; deploy approximatley 1000 PIT tags in mainstem and tributaries to support above efforts; maintain PIT tag antenna system in Asotin Creek; GPS redds when possible | 13698
2014-10-01 | 2015-09-30 | Expenses | cover direct costs of 1000-1300 PIT tags, reading scale samples for up to 700 juvenile steelhead, and miscellaneous supplie | 5488
subtotal WDFW |  |  |  | 20500