## ELR WorkPlan_100k option
Work Plan, Schedule and Estimated Costs by Task for the Asotin IMW - Oct 1, 2015 to Sept 30, 2016 assuming partial funding of $100,000**
Start Date | End Date | Task/Personnel | Description and Rational | Budget Request
Eco Logical Research Inc. - IMW Management, Coordination, Implementation and Synthesis
2015-10-01 | 2016-09-30 | Project Management, Data Management, Coordination, Data Analysis, and Reporting/ Project Manger; GIS, Statistical, and Database support staff | Management of overall project goals including coordination, permitting, budget and work plan development and tracking; manage PIT tag, fish capture data, PTAGIS and array resight data; coordinate with CHaMP to upload and analyze habitat data; manage LiDAR and aerial photography; provide monthly progress and annual reports; manage temperature and discharge data; synthesis and interpret data and test effectiveness of restoration using statistical models. | 42900
2015-10-01 | 2016-09-30 | Analyst | Data analyst to analyse all CHaMP, temperature, dishcarge, and fish data and to help develop models for testing effectiveness of restoration | 48943.03
2015-10-01 | 2016-09-30 | Fish and Habitat Monitoring/ Crew of one Sr and three Jr Technicians for 5 months | Monitor permanent sites for fish abundance, growth, survival, and movement, and habitat condition (CHaMP habitat protocol, photo documentation, rapid habitat surveys), maintain PIT tag arrays, temperature probes, water level gauges; conduct mobile fish surveys in winter and spring (5 field techs and 1 biologist) | 0
2015-10-01 | 2016-09-30 | Acquire, Purchase, Maintain equipment and supplies | Purchase or rent equipment to conduct surveys (5000 PIT tags and supplies, electrpshockers, seine nets, waders, total stations, mapgrade GPS, etc), travel and vehicle expenses, utilities (internet at field house and PTAGIS upload charges by QCI), accommodation and meals | 0
subtotal ELR |  |  |  | 91843.03
2015-10-01 | 2016-09-30 | RCO manages utility charges forPIT tag array infrastrucutre | Four power and phone line annual utility charges | 4200
sub-total Utilities payed by RCO |  |  |  | 4200
sub-total ELR, WDFW, and Utilities |  |  |  | 96043.03
2015-10-01 | 2016-09-30 | RCO overhead | RCO provides contract monitoring for the IMW project (4.12%) | 3956.9728
TOTAL |  |  |  | 100000.0028
** no field work is included in this budget. Data analysis and reporting are focus.