## ELR WorkPlan_ACCDPortion
Work Plan, Schedule and Estimated Costs by Task for the Asotin IMW - Oct 1, 2016 to Sept 30, 2017*
Start Date | End Date | Task/Personnel | Description and Rational | Cost* | Unit | Number of Units | Budget Request
Eco Logical Research Inc. - IMW Management, Coordination, Implementation and Synthesis
2016-10-01 | 2017-09-30 | Project Management, Data Management, Coordination, Data Analysis, and Reporting/ Project Manger; GIS, Statistical, and Database support staff | Management of overall project goals including coordination, permitting, budget and work plan development and tracking; manage PIT tag, fish capture data, PTAGIS and array resight data; coordinate with CHaMP to upload and analyze habitat data; manage LiDAR and aerial photography; provide monthly progress and annual reports; manage temperature and discharge data; synthesis and interpret data and test effectiveness of restoration using statistical models. | 82.5 | hours | 320 | 26400
2016-10-01 | 2017-09-30 | Analyst | Data analyst to analyze all CHaMP, temperature, discharge, and fish data and to help develop models for testing effectiveness of restoration | 0 | hours | 783 | 0
2016-10-01 | 2017-09-30 | Field Monitoring Lead (Biologist) | supervise monitoring crew and collect fish and habitat data, maintain field databases, conduct mobile fish surveys in winter and spring | 0 | hours | 1044 | 0
|  | Field Monitoring Crew (5 technicians) | Monitor permanent sites for fish abundance, growth, survival, and movement, and habitat condition (CHaMP habitat protocol, photo documentation, rapid habitat surveys), temperature probes, water level gauges; (5 field techs and 1 biologist) | 17.6 | hours | 2425 | 42680
2016-10-01 | 2017-09-30 | Accommodation and Travel | Accommodation, flights, meals, vehicle expenses, and utilities (internet at field house and PTAGIS upload charges by QCI) |  |  | 1 | 4000
2016-10-01 | 2017-09-30 | Acquire, Purchase, Maintain equipment and supplies | Purchase or rent equipment to conduct surveys (PIT tags and supplies, electroshockers, seine nets, waders, total stations, mapgrade GPS, data loggers, office supplies) |  |  | 1 | 8920
subtotal ELR Wages, Overhead, Fringe, Equipment, Supplies, and Travel | [6 empty] | 82000
2016-10-01 | 2017-09-30 | ACCD Overhead/Administration | Funds to be administered through Asotin County Conservation District |  |  | 1 | 4000
TOTAL | [6 empty] | 86000
* Note this Scope of Work only covers the portion of Asotin IMW funding that is supported by the Salmon Recovery Funding Board and Administered by Asotin County Conservation District.