## Total_SOW
Combined Statement of Work (ELR, WDFW, Infrastructure), Schedule and Estimated Costs by Task for the Asotin IMW - June 1, 2017 to Sept 30, 2018
Start Date | End Date | Tasks/Expenses | Budget Request
2017-06-01 | 2018-09-30 | Eco Logial Research, Inc. - Management, Monitoirng Implementation, Data Management, and Reporting | 223858
2017-06-01 | 2018-09-30 | Asotin County Conservation District - Administration | 4142
2017-06-01 | 2018-09-30 | WDFW - Interrogation Site Maintenance, Scale Analysis, Support of Fish Surveys, and Mainstem PIT tagging Surveys | 26000
2017-06-01 | 2018-09-30 | Infrastructure - Maintenance, Replacement of three (3) PIT Tag Interrogation Sites | 145969
TOTAL |  |  | 399969
|  | PSMFC anticipated funding | 245760
|  | SRFB Request | 154209
399969
1

## Eco Logical SOW
Statement of Work, Schedule and Estimated Costs by Task for the Asotin IMW - June 1, 2017 to Sept 30, 2018
Start Date | End Date | Task/Personnel | Description and Rational | Budget Request
Eco Logical Research Inc. - IMW Management, Coordination, Implementation and Synthesis
2017-06-01 | 2018-09-30 | Project Management, Data Management, Coordination, Data Analysis, and Reporting/ Project Manger; GIS, Statistical, and Database support staff | Management of overall project goals including coordination, permitting, budget and work plan development and tracking; manage PIT tag, fish capture data, PTAGIS and array resight data; coordinate with CHaMP to upload and analyze habitat data; manage LiDAR and aerial photography; provide monthly progress and annual reports; manage temperature and discharge data; synthesis and interpret data and test effectiveness of restoration using statistical models. | 60000
2017-06-01 | 2018-09-30 | Analyst | Data analyst to analyse all CHaMP, temperature, dishcarge, and fish data and to help develop models for testing effectiveness of restoration | 55000
2017-06-01 | 2018-09-30 | Fish and Habitat Monitoring/ **** Crew of five Jr Technicians for 4 months and Biologist for 5 months | Monitor permanent sites for fish abundance, growth, survival, and movement, and habitat condition (CHaMP habitat protocol, photo documentation, rapid habitat surveys), maintain PIT tag arrays, temperature probes, water level gauges; conduct mobile fish surveys in winter and spring (5 field techs and 1 biologist) | 77000
2017-06-01 | 2018-09-30 | Accomodation, travel, meals, equipment and supplies | Purchase or rent equipment to conduct surveys (tagging supplies, electroshockers, seine nets, waders, total stations, mapgrade GPS, etc), travel and vehicle expenses, utilities (internet at field house and PTAGIS upload charges by QCI), accommodation and meals | 23000
sub-total ELR |  |  |  | 215000
2017-06-01 | 2018-09-30 | RCO overhead | RCO provides contract monitoring for the IMW project (~4.12%) | 8858
2017-06-01 | 2018-09-30 | Asotin County Conservation District | ACCD to administer the contract with Eco Logical Research | 4142
TOTAL |  |  |  | 228000
4297.8 | 21489 | 84129
15660 | 62640

## Fish&Wildlife SOW
Work Plan, Schedule and Estimated Costs by Task for WDFW Assistance for Asotin IMW - June 1, 2017 to Sept 30, 2018
Start Date | End Date | Task/Personnel | Description and Rational | Budget Request
Washington Department of Fish and Wildlife - subcontract to support IMW data gathering
2016-06-01 | 2018-09-30 | WDFW Management of data collected for IMW | Oversee tasks and manage data collected by WDFW for IMW; coordinate with IMW coordinator as needed; provide all data to IMW coordinator | 1314
2016-06-01 | 2018-09-30 | Monitoring | Conduct fish surveys at pre-defined upper sites in Charley, North Fork, and Sout Fork Creeks; assess fish movement on mainstem of Asotin Creek above and below Headgate dam; deploy approximatley 1000 PIT tags in mainstem and tributaries to support above efforts; maintain PIT tag antenna system in Asotin Creek; GPS redds when possible | 13698
2016-06-01 | 2018-09-30 | Expenses | cover direct costs of 1000-1300 PIT tags, reading scale samples for up to 700 juvenile steelhead, and miscellaneous supplie | 5488
2016-06-01 | 2018-09-30 | OVERHEAD |  | 5500
subtotal WDFW |  |  |  | 26000

## Asotin AFC ACM + ACBUpgrade
Washington Department of Fish and Wildlife
Asotin Creek IPTDS Upgrade
AFC and ACM
2017-03-10
1 | PERSONNEL |  |  |  |  | 4965.3
| Scientific Technician 4 | 0.45 | mo | @ | 4212 | 1895.4
| Scientific Technician 3 | 0.45 | mo | @ | 4200 | 1890
| Scientific Technician 2 | 0.45 | mo | @ | 2622 | 1179.9
| Total | 1.35 |  | Wages Subtotal |  | 4965.3
2 | LODGING/PER DIEM |  |  |  |  | 2130
| Scientific Technician 4 | 5 | night | @ | 142 | 710
| Scientific Technician 3 | 5 | night | @ | 142 | 710
| Scientific Technician 2 | 5 | night | @ | 142 | 710
| Total |  |  | Travel Subtotal |  | 2130
3 | Benefits |  |  |  |  | 2367.532
| OASI |  | salary | @ | 6.2% | 307.8486
| Retirement |  | salary | @ | 11.18% | 555.1205
| Labor and Industries | 1.35 | mo | @ | 161.16 | 217.566
| Health Insurance | 1.35 | mo | @ | 900 | 1215
| Medical Aide |  | salary | @ | 1.45% | 71.9969
| Total |  |  | Benefits Subtotal |  | 2367.532
4 | SUPPLIES/EQUIPMENT |  |  |  |  | 100735.1492
| Personnel Service Fee |  | salary | @ | 0.4058% | 20.1492
| 07309MM 1 ton Pickup | (1, 1500) | (mo, mile) | @ | ($315,$0.46) | 975
| Antenna Controller | 3 | ea | @ | 3500 | 10500
| Antenna Control Node (ACN) | 18 | ea | @ | 1425 | 25650
| ACN Backup | 3 | ea | @ | 1425 | 4275
| ACN HDPE Antenna | 18 | unit | @ | 900 | 16200
| Backup ACN HDPE Antenna | 2 | unit | @ | 900 | 1800
| ACN Canister | 20 | unit | @ | 150 | 3000
| CAN bus cabling | 900 | feet | @ | 3.6 | 3240
| Power Supply and Enclosure | 3 | unit | @ | 1900 | 5700
| Earth Anchors | 345 | ea | @ | 75 | 25875
| Anchor Straps | 700 | ea | @ | 5 | 3500
|  |  |  | Supplies/Equipment Subtotal |  | 100735.1492
5 | OVERHEAD / INDIRECT | 32.46% |  |  |  | 35770.2647
6 | SUB-TOTAL |  |  |  |  | 145968.2459
7 | PROJECT MANAGEMENT/ADMIN
| Asotin County Conservation District | ACCD to administer the contract with Eco Logical Research |  |  |  | 4142
Total | [5 empty] | 150110.2459
Complete SOW for Asotin IMW 2017
| Eco Logial Research, Inc. - Management, Monitoirng Implementation, Data Management, and Reporting |  |  |  |  | 223858
| Asotin County Conservation District - Administration |  |  |  |  | 4142
| WDFW - Interrogation Site Maintenance, Scale Analysis, Support of Fish Surveys, and Mainstem PIT tagging Surveys |  |  |  |  | 26000
| Infrastructure - Maintenance, Replacement of three (3) PIT Tag Interrogation Sites |  |  |  |  | 145969
[5 empty] | Total | 399969
For PRISM
| SRFB Request |  |  |  |  | 150110 | 177000
| Match |  |  |  |  | 26890 | 15.19%
[5 empty] | Total | 177000
Note on B26: Crawford: I've adjusted amounts for equipment but that is all; no adjustments to staffing/fringe. And skipped some extras. The cost/numbers of earth anchors and straps is somewhat suspect to me. But I will double check with our Antenna shop in Wenatchee, and hopefully get back to you early next week.