FBRB FINAL APPLICATION QUESTIONS

1. Limiting Factors

Describe how the proposed project addresses limiting factors to productivity and life history stages within the watershed. Limit 500 words.

This project is one part of a multi-year, multi-phase effort to improve fish passage in the Mill Creek flood control channel. This is a construction phase, which will improve passage for about 2,500 feet, or about one-quarter of the length of the concrete channel.

A flood control project completed in the 1940s modified the Mill Creek channel for about seven miles through Walla Walla. The uppermost mile of the flood control project remains federal property, owned and operated by the Corps of Engineers. The lower six miles was turned over to the Mill Creek Flood Control Zone District, and is operated and maintained by Walla Walla County Public Works Department. Two miles of the non-federal channel is a concrete lined flume.

Upstream of the flood control project is over 50 miles of Mill Creek and headwater tributaries that provide good to excellent habitat. Fish managers believe that more fish should be produced in the upper Mill Creek system, and that passage through the flood control project is the problem.

The Mill Creek Fish Passage Assessment (SRFB #06-2203) identified flow-dependent barriers in the Mill Creek flood control channel. In the concrete flume section (subject of this project), existing conditions present unfavorable hydraulic (depth and velocity) conditions. Migrating adults experience velocities measured at up to 12 feet per second, with no resting areas in the two-mile concrete segment. During summer low flow, supercritical flow (accelerated, shallow flow) around the channel baffles prevents volitional passage of juveniles, at a time when water temperatures are high, and access to cool water refugia is critical. 

The nature of the problem can be difficult to fully describe. Following the completion of the passage assessment, the situation could be summed up by saying that, at any given flow, there is a barrier somewhere in the concrete channel, and that any section of the channel is a barrier at some flow. 

The project design addresses the velocity problem by adding channel roughness to create a zone of lower velocity water suitable for sustained swimming speeds of adult salmonids. Resting pools provide low velocity areas where fish can hold to regain energy or when flow exceeds the design criteria (roughness functions up to about 320 cfs). Supercritical flow around baffles is eliminated by removing existing baffles, and adding new baffles at a spacing which backwaters each baffle.

The design was refined in a physical model study prior to the first construction project. The degree of roughness (to create the desired velocity), pool size and shape, and baffle spacing were all tested. Further design verification is conducted at the completion of each construction phase. The concept has been measured to perform as designed.

2. Level of Coordination

Describe the level of coordination of the proposed project with other recently completed or ongoing restoration projects within the watershed. (Note: this can be any type of habitat restoration, e.g., large wood placement or floodplain restoration.) Limit 500 words.

Passage work on the Mill Creek flood channel has been going on for over 10 years. Completed and scheduled projects are:

2011 – Mill Creek Fish Passage – Flume Transitions (RCO #09-1587) – Applied passage concept to 200 feet at the lower end of the concrete channel, and to 50 feet at the upper end of the concrete channel.

2013 – Mill Creek Fish Passage – Reach Type 6 (RCO #11-1587) – Applied passage concept to 350 feet of channel near mid-channel.

2016 – Mill Creek Fish Passage – 9th Ave Extension (RCO #13-1387) – Applied passage concept to 1,050 feet of channel, continuous with the 2011 project at the downstream end of the channel.

2017 – Mill Creek Fish Passage – Upper Flume Design (RCO #15-1324) – Completed final designs for the upper 5,000 feet of the concrete channel.

2019 – Mill Creek Fish Passage – Park to Otis (RCO #17-1305) – Will apply fish passage design to 930 feet of the concrete channel. This is the lower end of the Upper Flume plan set.

2020 – Mill Creek Passage Design – 6th Ave Extension (RCO #18-2090) – Will complete final design for about 1,285 feet of concrete channel, continuous with the 9th Ave Extension project.

2021 – Mill Creek Passage Design – Spokane to Park (RCO #19-1614) – Will complete final designs from the Reach Type 6 project to the Park to Otis project.

2021 – Mill Creek Fish Passage – Division to Roosevelt (RCO #19-1613) – Will apply fish passage concept to about 2,500 feet of channel, connecting to the upper end of the flume.

Projects through 2019 will have treated about 2,500 feet at a total cost of $3,329,293. Completion of the Division to Roosevelt project in 2021 will bring the total to about 5,000 feet, which is approximately half of the concrete channel.

Project partners include Salmon Recovery Funding Board, Snake River Salmon Recovery Board, The Confederated Tribes of the Umatilla Indian Reservations, Bonneville Power Administration, Washington Department of Fish and Wildlife, Walla Walla County, and the Brian Abbott Fish Barrier Removal Board.

3. Project Scope

Describe the scope of the proposed project, and the goals and objectives. Describe how the project scope is appropriate to meet the identified goals and objectives. Include milestones and schedule. Limit 500 words.

Project Scope: 
To apply the fish passage concept to 2,500 feet of the channel. To do so, some of the existing concrete will be saw-cut and removed. The underlying grade will be adjusted by excavation and placement of bedding gravel. Pre-cast “roughness panels” will be placed. Resting pools and new baffles will be formed and cast in place.

Goals: 
1. Improve low flow passage for juvenile and adult steelhead, bull trout, and spring chinook

2. Improve high flow passage for adult steelhead, bull trout, and spring chinook

3. Provide resting opportunities where none currently exist

Objectives: 
1. Reconfigure concrete baffles– remove and replace with new layout to eliminate supercritical flow.

2. Install surface roughness to provide a low velocity boundary layer for discharges up to 320 cfs.

3. Install resting pools.

Project Schedule: 
Fall 2019 – Submit permit applications.
Fall 2020 – Conduct construction bid process for Division to Roosevelt section. 
Early 2021 – Award construction contract for Division to Roosevelt.
June – September 2021 – Division to Roosevelt construction.

4. Additional Supporting Information

Provide any other relevant information you would like for the Board to consider in the evaluation of the proposed project, e.g., the proposed project’s contribution to an approved recovery plan. Limit 1,000 words.

The Snake River Salmon Recovery Plan for SE Washington identifies Mill Creek as a major spawning area for summer steelhead.  In Chapter 5 of the Recovery Plan (Section 5.5.2.3 pg 155-156), the flood control channel is described, and Plan states “It is believed to be extremely difficult for an adult salmon or steelhead under its own power to pass from Gose Street to Bennington Dam.” The Current Impacts and Limiting Factors section for Mill Creek states, “The Mill Creek steelhead population continues to be suppressed by reduced habitat diversity, key habitat, and obstructions.” The proposed project is also located in the designated critical habitat for bull trout (50 CFR 17. 2010. pg 63,898).

Though passage for adults should lead to better production, access to historical habitats is critical in addressing the spatial structure component of recovery goals. The Middle Columbia Steelhead ESA Recovery Plan rates the Walla Walla River spatial structure/diversity risk as moderate (Mill Creek is within the Walla Walla watershed). Both the Snake River Salmon Recovery Plan and the Middle Columbia Steelhead Recovery Plan point to the need for improved passage in Mill Creek.

The Mill Creek Work Group is a stakeholder group composed of managers and technical professionals, representing federal, state, local, and tribal government and non-governmental organizations. The Work Group actively supports the Mill Creek fish passage projects, and has been the guiding body for all of the passage efforts on Mill Creek, beginning with the initial fish passage assessment. The Work Group is updated regularly on passage progress, and provides direction on future actions.

The Upper Flume project reach is considered as five sections: Park to Otis, Otis to Merriam, Merriam to Clinton, Clinton to Division, and Division to Roosevelt. After meeting with FBRB staff and touring Mill Creek, we decided to pursue the Park to Otis (match contribution) and Division to Roosevelt (funding request) segments. Dense residential development makes channel access a difficult problem for the other Upper Flume segments.