Planning Milestone Worksheet

Project Number: 19-1584

Project Name: Chumstick Creek Culverts – RM 0.52 and RM 1.48

Sponsor: Chelan County Natural Resources Department

Grant Manager: Amee Bahr

RCO uses the milestones worksheet to create the starting and ending dates for your project and to identify important project milestones that will help your project stay on schedule. These milestones should be realistic, attainable and allow for quick implementation and expenditure of grant funds.

Instructions:

- In the Target Date column, identify the estimated date that you expect to complete the milestone. If the milestone has already been completed put in the date it was completed. If it is not applicable to your project, please put N/A in the date field.

- Use the Comments/Description column to write in comments that will assist in describing the milestone. Examples are: permits in hand; property acquired under RCO waiver; in-water work window; etc.

| Milestone | Target Date | Comments Description |
| --- | --- | --- |
| Project Start | 7/1/2019 |  |
| Data Gathering Started | 7/1/2019 | Eligible pre-agreement expenses per Manual 5 |
| Draft Design to RCO |  |  |
| Draft Plan to RCO |  |  |
| RFP Complete/Consultant Hired | 11/01/2020 |  |
| Progress Report Submitted | 05/15/2020 |  |
| Preliminary Design to RCO | 1/15/2020 |  |
| Applied for Permits | 2/14/2020 |  |
| Cultural Resources Complete | 6/30/2020 | (If Ground Disturbing Activities) |
| Finalize Contract/Bid documents | 05/30/2020 |  |
| Progress Report Submitted | 10/15/2020 |  |
| Final Design to RCO | 03/02/2020 | Preliminary Design deliverables as described in Appendix D Manual 18 |
| Permits Complete | 6/30/2020 | Not a grant deliverable. |
| Progress Report Submitted |  |  |
| Milestone | Target Date | Comments Description |
| Progress Report Submitted |  |  |
| Final Plan to RCO |  |  |
| Final Report in PRISM |  |  |
| Agreement End Date | 01/30/2020 | 24 months from funding date. PROJECT CLOSING. All expenditures must be prior to this date. |
| Final Billing to RCO | 12/30/2020 | Provide your final invoice and report within 60 days of Agreement End Date. |