Restoration Milestone Worksheet

Project Number and Name:	19-1584

Sponsor: Chumstick Creek Culverts – RM 0.52 and RM 1.48

Sponsor Project Contact: Allison Lutes – Habitat Program Manager

SRFB Project Manager: 	Amee Bahr

The milestones worksheet is used by RCO to create the starting and ending dates for your project and to identify important project milestones that will help your project stay on schedule.  These milestones should be realistic, attainable and allow for quick implementation and expenditure of grant funds.

Instructions:

- In the Target Date column, identify the estimated date that you expect to complete the milestone.  If the milestone has already been completed put in the date it was completed.  If it is not applicable to your project please put N/A in the date field or delete the milestone.

- Use the Comments/Description column to write in comments that will assist in describing the milestone.  Erase the existing text first. Examples are: permits in hand; property acquired under RCO waiver; in-water work window; etc.

| Milestone | Target Date | Comments Description |
| --- | --- | --- |
| I have checked the Authorizing Resolution attached to the project in PRISM and (check one): The correct individual is listed as signatory for the agreement. The form must be resubmitted with the correct individual listed as the signatory for the agreement. |  |  |
| Project Start | 7/1/2019 |  |
| Preliminary Design to RCO | 01/15/2020 | If not provided with application; Manual 18, Appendix D-2 |
| Final Design to RCO | 4/01/2020 | If required; Manual 18, Appendix D-3 |
| Cultural Resources Complete | 6/30/2020 | Must occur prior to beginning ground disturbance and the restoration start date milestone |
| Applied for Permits | 03/15/2020 |  |
| Permits Complete | 06/30/2020 |  |
| Landowner Agreement to RCO (required if project occurs on land NOT owned by sponsor) | 06/01/2020 | Must be before restoration start date milestone. |
| Bid Awarded / Contractor Hired | 6/30/2020 |  |
| Restoration Started | 8/15/2020 |  |
| Annual Project Billing | 6/30/2020 | And at least once per year |
| Progress Report Submitted | 5/15/2020 10/15/2020 | Every 6 months (minimum 2 per year) |
| Restoration Complete | 10/15/2020 |  |
| As-built drawings to RCO | 11/13/2020 | Per Manual 18, Appendix D-4 |
| Funding Acknowledgement Sign (SRFB) Posted | N/A |  |
| Stewardship Plan to RCO (Required if project occurs on sponsor-owned land) |  |  |
| RCO Final Inspection | 11/30/2020 |  |
| Final Billing to RCO | 12/30/2020 | Up to 90 days from Agreement End Date to submit final invoice |
| Final Report in PRISM | Must be on or after final bill | This is the RCO final report in PRISM (up to 90 days following agreement end date) |
| Agreement End Date | 01/30/2020 | PROJECT CLOSING. All expenditures must be prior to this date. |
| [Special Condition] |  | Only if project conditioned by review panel or grant manager |
| [insert other milestones, as needed] |  |  |