## Sheet1
Project: | Motteler Road Culvert Replacement - Chumstick Creek RM 0.52
Project Engineer: | Waterfall Engineering, Pat Powers (waterfallengineering@comcast.net)
Project Manager: Allison Lutes, CCNRD (allison.lutes@co.chelan.wa.us/509-679-7095
Designs Sent out for Comment: 10/23/2020
Comment No. | Sheet No. | Comment | Comment From (Agency or Entity) | Response | Item Updated Date
1 | 6 of 8 | DFW recommends pulling back rip rap to only interact with Q2. | WDFW - Roler
2 | 6 of 8 | Add channel banks to stream cross section as to not construct a plane bed channel. We are looking for more complex channel cross section including a low flow channel. | WDFW - Roler
3 | 6 of 8 | After adding channel banks to the design, the Q100 will need to be re-evaluated. | WDFW - Majsterek
4 | 6 of 8 | Is the 16ft channel width matching a BFW measured in a reference reach? Please make a note of BFW on the drawings. | WDFW - Roler
5 | 8 of 8 | Could root-wads be incorporated into the design to add complexity and provide additional slope stability? | WDFW - Roler
6 | n/a | The recommended work window for Chumstick Creek is from the middle of July to the end of September. | WDFW - Barg