## ELR WorkPlan_15-1443
Exhibit A: Work Plan, Schedule and Estimated Costs by Task for the Asotin IMW - January 1, 2021 to December 31, 2021
| Start Date | End Date | Task/Personnel | Description and Rational | Cost | Unit | Number of Units | Budget Request
| 2021-01-01 | 2021-12-31 | Analyst | Data analyst to analyze all juvenile steelhead emigration and smolts/spawner | 53.91 | hours | 391.5 | 21105.765
| 2021-05-01 | 2021-09-30 | Restoration enhancement and maintenance | Crew of 5 technicians to construct 40-60 low-tech structures | 6000 | week | 3.5 | 21000
| 2021-05-01 | 2021-09-30 | Equipment and supplies | Post-driver, trucks, trailers, atvs, chainsaws, travel, and miscellaneous | 1500 | - | 1 | 1500
| 2021-01-01 | 2021-07-15 | Acquire a Cultural Survey | Subcontract a cultural survey on North Fork Asotin Creek | 5000 | - | 2 | 10000
| PROJECT TOTAL | [6 empty] | 53605.765