## ESRP Amendment Request Information

**Amendment Type** *(Check box for type(s) of amendment requested.)*

[ ]  Scope (*change of location, change in metrics*)

[x]  Time extension

[x]  Cost (*increase, decrease, match change*)

|  |  |
| --- | --- |
| Project name | **Seahorse Siesta Barge Removal** |
| Project number | **16-1306 / 18-2062** |
| Date of request | **9/8/2021** |
| Sponsor(s) | **Northwest Straits Foundation** |
| Current end date | **12/31/2021** |

**Funding** (*Grants manager may need to provide information for this section*)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Current Amount** | **Share** | **Biennium/ Year of Funding** | **Amount Remaining** | **Proposed Funding Amount[[1]](#footnote-1)** | **Proposed Share** |
| Funding source: ESRP | $56,815 | 6.99% | 2018 | $34,716.82 | $66,815 | 8.1% |
| Funding source: PSAR | $454,028 | 56.86% | 2016 |  |  |  |
| Funding source: Salmon Fed | $218,000 | 26.82% |  |  |  |  |
| Sponsor match | $84,000 | 10.33% |  | $ | $ | % |
| Project total | $812,843 | 100% |  | $ | $ |  |

**All Requests**

* Brief project summary: The project proposed to remove a large barge and bulkhead structure from the toe of a feeder bluff located north of Langley, Whidbey Island. The removal uncovered 10,800 SF of potential sand lance and surf smelt habitat. Forage fish surveys conducted prior to restoration identified sand lance eggs within the area of the restoration.
* Current project progress: Construction was completed as of March 2021. The first phase of vegetation was also installed in March 2021. Miscellaneous debris from the demolition has resurfaced as tides move sediment around. The contractor will return to the site on September 10th for a final clean up.

**Time Extensions**

* Reason and justification for delay: The project experienced significant delays due to Covid-19 related contracting as well as unforeseen conditions once the project began. We anticipate additional miscellaneous debris may resurface therefore are requesting an extension to allow for potential removal one more time in summer 2022. We would also like one more season to monitor and manage the vegetation to ensure successful growth of the riparian zone.
* Proposed new project milestones (*include any uncertainties)*:
	+ Monitoring report: 12/31/2021
	+ Progress Report: 12/31/2021; 6/30/2022
	+ Final Report/New End Date: December 31, 2022
* Number of time extensions that have been previously requested for this project: 0

**Cost Increases**

* Reason and justification for cost increase (*include any uncertainties*):
* Actions taken to control costs or limit the cost increase: (*include any other funding sources pursued*)
* Number of cost increases that have been previously requested for this project:

**Scope Changes**

* Description of, and reason for, scope change:
* **Acquisition projects:** see [Manual 3](https://www.rco.wa.gov/wp-content/uploads/2019/07/Manual3.pdf), Section 7 for specific scope change requirements and questions.

**Attach map, if relevant.**

1. Fill out only if requesting a change in RCO funding or match. [↑](#footnote-ref-1)