## Sheet 1
Family Forest Fish Passage Program | [5 empty] | Revised 10/10/08
Culvert Cost Estimate Template
Project Name: | ICPWD Culvert #1894
RCO Project #: | 19-1343
Date: | 2021-09-23
Estimate By: | Whidbey Island Conservation District
Stream: | Unnamed trib of Race Lagoon
Proposed Correction: | Replace existing culvert with a 66'x7'x4.5' No Slope concrete box culvert. Includes water line relocation (if needed).
Description | Unit | CAD Quantity | Mult | Bid Quantity | Cost | Amount | Sub Total | Notes
Mobilization
Mobilize | L.S. | 1 |  |  | 19000 | 19000 |  | 10% of construction total
Access | L.S. | 1 |  |  | 500 | 500
Stream Bypass | L.S. | 1 |  |  | 2000 | 2000 |  | Minimal: creek likely dry in summer
Clear and Grub | L.S. | 1 |  |  | 1000 | 1000
Dewater (Pumps, Etc) | L.S. | 1 |  |  | 1000 | 1000 |  | Creek likely dry in summer but dewatering may still be needed
Fish Removal | L.S. | 0 |  |  | 2000 | 2000 |  | Assumes creek dry in summer
Creek may be dry in summer
MOBILIZATION SUB TOTAL | [6 empty] | 25500
Excavate
Common Excav. and Disposal | C.Y. | 290 | 1.2 | 348 | 22 | 7656
Roadway Excavation and haul | C.Y. | 23 | 1.2 | 27.6 | 35 | 966
Remove & Dispose Culvert | ea. | 1 | 1 | 1 | 500 | 500
EXCAVATION SUBTOTAL | [6 empty] | 9122
Utility Relocation
6" water main relocation | L.F. | 20 | 1.5 | 30 | 100 | 3000 |  | need to verify location
Phone line relocation | L.S. | 1 | 1 | 1 | 3000 | 3000 |  | need to verify location
UTILITY RELOCATION SUBTOTAL | [6 empty] | 6000
Culvert Installation
Bedding | C.Y. | 11 | 1.2 | 13.2 | 65 | 858
Streambed Gravel | C.Y. | 16 | 1.2 | 19.2 | 125 | 2400
Riprap | C.Y. | 5 | 1.2 | 6 | 65 | 390
Concrete box culvert 7'x4.5' | L.F. | 66 | 1 | 66 | 1800 | 118800
Install Culvert | L.S. | 1 | 1 | 1 | 15000 | 15000
Wing Walls | L.S. | 1 | 1 | 1 | 6000 | 6000
Structural Backfill, Compaction | C.Y. | 90 | 1.3 | 117 | 65 | 7605
CULVERT INSTALLATION SUBTOTAL | [6 empty] | 151053
Road Work
Crushed Surfacing | C.Y. | 16 | 1.3 | 20.8 | 65 | 1040
Hot Mix Asphalt | Ton | 11 | 1.2 | 13.2 | 160 | 2112
HMA Saw Cut & Seal | L.F. | 52 | 1 | 52 | 20 | 1040
Line Painting | L.F. | 30 | 1 | 30 | 4 | 120
Traffic Control | L.S. | 1 | 1 | 1 | 10000 | 10000
ROAD WORK SUBTOTAL | [6 empty] | 14312
TESC, Stream Channel and Site Restoration
Streambed Mix | C.Y. | 8 | 1.2 | 9.6 | 125 | 1200
LWD | L.S. | 1 | 1 | 1 | 5000 | 5000
Revegetation | L.S. | 1 | 1 | 1 | 5000 | 5000
TESC | L.S. | 1 | 1 | 1 | 5000 | 5000
Top Soil | C.Y. | 6 | 1.2 | 7.2 | 40 | 240
Seed, Fertilize, Mulch | S.Y. | 40 | 1.2 | 48 | 3 | 120
Final Site Cleanup | L.S. | 1 | 1 | 1 | 2000 | 2000
TESC AND CHANNEL RESTORATION SUB TOTAL | [6 empty] | 18560
CONSTRUCTION SUB TOTAL | [6 empty] | 224547
Sales Tax | 8.1% | [5 empty] | 18188.307
CONSTRUCTION | [6 empty] | 242735.307
Engineering | 25% | [5 empty] | 60683.8268
Admin/Planning | 15% | [5 empty] | 36410.296
Geotech Investigation & Design | 10% | [5 empty] | 24273.5307
Permit Fees | [6 empty] | 1500
PROJECT TOTAL | [6 empty] | 365602.9605
Please email completed form to Laura Till, WDFW. tilllet@dfw.wa.gov Questions? Call Laura at 360-902-2352