## Project Budget Worksheet
| Project Name | Meadowdale: Informing Coastal Stream Restoration PRISM # 22-17
| Project Sponsor | The Tulalip Tribes
|  |  | Total Cost | ESRP Funding |  |  | Match | Unsecured | Estimated Total Costs | [5 empty] | Match
# | Task List | Target Date | Total Cost | Past Award(s) | Current Request | ESRP Total | Total Match | Unsecured | Personnel | Fringe | Travel | Equipment | Supplies | Contractual | Sponsor cash/in-kind | Snohomish County | Source B | Source C | Source D | Source E | Source F | Source G
1 | Project Administration | 2025-09-30 | 22343 |  | 7343 | 7343 | 15000 | 0 | 1905 | 438 |  |  |  | 20000 |  | 15000
2 | Project Plan | 2023-10-31 | 5843 |  | 5843 | 5843 | 0 | 0 | 1905 | 438 |  |  |  | 3500
3 | Wiki Content | 2025-07-01 | 3906 |  | 3906 | 3906 | 0 | 0 | 1143 | 263 |  |  |  | 2500
4 | Data Collection and Processing | 2025-06-30 | 117201 |  | 71883 | 71883 | 45318 | 0 | 48708 | 11860 | 400 | 3360 | 250 | 52623 | 30318 | 15000
5 | Interim Results Analysis | 2025-02-28 | 26513 |  | 26513 | 26513 | 0 | 0 | 5262 | 1251 |  |  |  | 20000
6 | Final Project Report | 2025-08-31 | 11513 |  | 11513 | 11513 | 0 | 0 | 5262 | 1251 |  |  |  | 5000
7 | Final Project Presentation | 2025-09-30 | 2668 |  | 2668 | 2668 | 0 | 0 | 1343 | 325 |  |  |  | 1000
| Indirect Expenses (optional) (19.69%) |  | 10152 |  | 10152 | 10152 | 0 | 0 | 8117 | 1926.4 | 59 |  | 49.225
| TOTAL |  | 200138.625 | 0 | 139821 | 139821 | 60318 | 0 | 73645 | 17752.4 | 459 | 3360 | 299.225 | 104623 | 30318 | 30000 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Dedicated Match Amount >> | 60318
[6 empty] | Retainage >> | 15000
[6 empty] | Dedicated Match Percent >> (must exceed 30%) | 43.14%
Note on B10: ESRP - Use the [Data Collection Schedule Tab] to Estimate Costs
Note on E6: TishCC: Indicate the amount of past awards tfrom ESRP that contributed to this project.
Note on F6: TishCC: Indicate the amount this project is requesting from ESRP currently
Note on H17: Under ESRP Terms and Conditions, 10% or $15,000 is retained until until all deliverables are received.
Note on J5: TishCC: This is intended to capture the entire project need including current request.
Instructions:
1. Only enter values into white boxes--all other boxes are calculated and locked. The password to unlock the sheets is 'ESRP'
2. Verify that the task list is suited to project scope by referring to the standard ESRP Scope of Work. To alter the task list, unlock the sheet, insert rows, and paste formula into the newly created calculated fields. This sheet is intended to expand to include all tasks over the life of the project for multi-award projects.
3. First, Define estimated whole project costs by object class (Blue). The blue columns, summed in column D describes the cost of implement the planned project--including ESRP funds, match, AND any other leveraged funds.
4. Use the enclosed Data Collection Schedule (second tab) to define data collection cost over time by ecosystem component.
5. Indicate your ESRP Request by task, including past awards if this is part of a portfolio request (Peach).
6. Indicate additional sources of funding necessary to implement the whole project, and indicate if funding is secured or speculative. Explain any unmet need or speculative funding in the budget narrative (Green).
7. Identify the source(s) of dedicated non-state match (purple arrow). Verify that 30% match target is being met (cell H17).
8. If you have questions, Tish.Conway-Cranos@dfw.wa.gov
9. In order to describe multi-award projects, You will need to modify the worksheet by adding tasks and modifying the data collection schedule in the future.
10. To export to SOW, Select ExportToSOW in the object pull down menu (A4:I18), then copy and paste to the SOW. You will need to format to fit the page and reduce font size in your word processor.
Total Project Costs
Total Leverage
Dedicated Match to ESRP

## Data Collection Schedule
|  | Data Collection Budget | [6 empty] | Estimated Cost Over Time
Component | Total Cost | Personnel | Fringe | Travel | Equipment | Supplies | Contractual | Sum of Cost Over Time | 2021 | 2022 | 2023 | 2024 | 2025 | 2026
4.1 Beach & Embayment Transects | 16708 | 10143 | 2415 | 100 |  | 50 | 4000 | 16708 |  |  | 2784.6667 | 8354 | 5569.3333
4.2 RFID PIT Tagged gravel tracking | 20218 | 10143 | 2415 | 100 | 3360 | 200 | 4000 | 20218 |  |  | 6065.4 | 10109 | 4043.6
4.3 Aerial imagery acquisition (UAV flights) | 5207 | 4119 | 988 | 100 |  |  |  | 5207 |  |  | 1487.7143 | 2231.5714 | 1487.7143
4.4 Sediment mapping and classification | 10000 | [5 empty] | 10000 | 10000 |  |  | 2857.1429 | 4285.7143 | 2857.1429
4.5 Biological Sample Analysis | 19750 | [5 empty] | 19750 | 19750 |  |  |  |  | 19750
4.6 (MATCH) Water quality data logger installation and maintenance | 2499 | 2014 | 485 |  |  |  |  | 2499 |  |  | 833 | 833 | 833
4.7 (MATCH) Time-lapse camera installation and maintenance | 10164 | 5771 | 1420 | 100 |  |  | 2873 | 10164 |  | 2541 | 2541 | 2541 | 2541
4.8 (MATCH) Fish sampling | 12496 | 10072 | 2424 |  |  |  |  | 12496 |  |  | 4165.3333 | 4165.3333 | 4165.3333
4.9 (MATCH) Invertebrate Sampling | 5159 | 4138 | 1021 |  |  |  |  | 5159 |  |  | 1719.6667 | 1719.6667 | 1719.6667
4.10 (MATCH) Snohomish County Data Collection and Analysis | 15000 | 2308 | 692 |  |  |  | 12000 | 15000 |  |  | 5000 | 7500 | 2500
TOTAL | 117201 | 48708 | 11860 | 400 | 3360 | 250 | 52623 | 117201 | 0 | 2541 | 27453.9238 | 41739.2857 | 45466.7905 | 0
Note on I4: Red text indicates that cost over time does not match budget
Instructions:
1. Only enter values into white boxes--all other boxes are calculated and locked. Use the password, 'ESRP' to unlock the worksheet only if necessary.
2. Develop data collection budget (in turquoise) by ecosystem component.
3. Estimate cost over time by Calendar Year (dusky pink)
4. Check 'Sum of Cost over Time'--if text is red, cost over time does not match budget.
5. Sum of Cost over Time provides a shared expectation between the project proponent and ESRP Staff
6. Color coding in the Estimated Cost over Time simply describes relative distribution of costs
7. If you have questions, contact Tish.Conway-Cranos@dfw.wa.gov

## Summary
Project Name | Project Sponsor | ESRP Request | Total Cost | Dedicated Match | Leverage | Final Report Date
Meadowdale: Informing Coastal Stream Restoration PRISM # 22-17 | The Tulalip Tribes | 139821 | 200138.625 | 60318 | 60318 | 2025-09-30
For Administrative Use Only