## Amendment Request Information[[1]](#footnote-1)

**Amendment Type** *(Check box for type(s) of amendment requested.)*

Scope (*change of location, change in metrics*)

Time extension

Cost (*increase, decrease, match change*)

|  |  |
| --- | --- |
| Project name | **Race Lagoon Passage – Culverts #1893 &1894** |
| Project number | **22-1089** |
| Date of request | **2/15/2024** |
| Sponsor(s) | **SFEG** |
| Lead Entity | **Skagit** |
| Current end date | **3/22/2024** |

**Funding** (*Grants manager may need provide information for this section*)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Current Amount** | **Biennium/ Year of Funding** | **Amount Remaining** | **Share** | **New Funding Amount** | **New Share** |
| Funding source (*add lines for separate funds*) | $149,468 | 21/23 | $102,135 | %100 | $NA | %NA |
| Sponsor match | $ |  | $ | % | $ | % |
| Project total | $149,468 |  | $ |  | $ |  |

**All Requests**

* Brief project summary: replace two fish barrier culverts, culvert 1893 and 1894, under Race Road near Coupeville, WA and a private crossing immediately downstream of Culvert #1894
* Current project progress: All project deliverables will be finalized by 3/22/2024.
* **Time Extensions**
* Reason and justification for delay: An extended end date to 9/22/2024 will allow time to spend down remaining funds and progress project to next stage (Final Design)
* Proposed new project milestones (*include any uncertainties)*: Fish Study finalizes by 9/25/2024, End date on 9/22/2024, all associated end of term deliverables (final report etc) due by 12/22/2024.
* Number of time extensions that have been previously requested for this project: 0

**Cost Increases: NA**

* Reason and justification for cost increase (*include any uncertainties*):
* Actions taken to control costs or limit the cost increase: (*include any other funding sources pursued*)
* Number of cost increases that have been previously requested for this project:

**Scope Changes: NA**

* Description of, and reason for, scope change:
* **Acquisition projects:** see [Manual 3](https://www.rco.wa.gov/wp-content/uploads/2019/07/Manual3.pdf), Section 7 for specific scope change requirements and questions.

**Attach documentation of lead entity approval: NA**

**Attach map if relevant.**

1. Please use the amendment matrix in Manual 18 to determine if a request needs lead entity approval. For cost increases using Puget Sound Acquisition and Restoration funds, provide this template to the Puget Sound Partnership for its approval. [↑](#footnote-ref-1)